## WP1
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | 0 | [6 empty] | 58746.6667 | [5 empty] | 88120 | [5 empty] | 88120 | [5 empty] | 88120 |  | 29373.3333 |  |  | 0 | 352480 | 352480 | TECNOL1 M5-28 per tot 24 PM | IM M5-28 per tot 24 PM | FUNZ M5-28 per tot 24 PM
CNR-IFN@MI | [30 empty] | 0 | 0 | 0
CNR-IFN@TN | [30 empty] | 0 | 0 | 0
CNR-IMM@BO | [30 empty] | 0 | 0 | 0
CNR-IMM@CT | [17 empty] | 25080 | [5 empty] | 25080 | [5 empty] | 25080 | 0 | 75240 | 75240 | TECNOL1 M13-30 per tot 18 PM
CNR-ISM | [30 empty] | 0 | 0 | 0
CNR-NANOTEC | [30 empty] | 0 | 0 | 0
CNR-SPIN | [30 empty] | 0 | 0 | 0
AREA | [9 empty] | 12771 | [5 empty] | 25542 | [14 empty] | 0 | 38313 | 38313 | PM M8-10+M11-16 per un tot di 3+6 PM
POLIFAB | [30 empty] | 0 | 0 | 0
UNIMI | [30 empty] | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58746.6667 | 0 | 12771 | 0 | 0 | 0 | 88120 | 0 | 25542 | 0 | 25080 | 0 | 88120 | 0 | 0 | 0 | 25080 | 0 | 88120 | 0 | 29373.3333 | 0 | 25080 | 0 | 466033 | 466033
FLUSSO | 0 |  | 0 |  | 0 |  | 58746.6667 |  | 12771 |  | 0 |  | 88120 |  | 25542 |  | 25080 |  | 88120 |  | 0 |  | 25080 |  | 88120 |  | 29373.3333 |  | 25080 |  |  |  | 466033
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 62858.9333 |  | 13664.97 |  | 0 |  | 94288.4 |  | 27329.94 |  | 26835.6 |  | 94288.4 |  | 0 |  | 26835.6 |  | 94288.4 |  | 31429.4667 |  | 26835.6 |  | 0 |  | 498655.31
IO | [6 empty] | IO1 |  | IO2 |  |  |  | IO3 |  | IO4 |  | IO5 |  | IO6 |  |  |  | IO7 |  | IO8 |  | IO9 |  | IO10
Deliverables | [6 empty] | D1.1 |  | D1.2 |  |  |  | D1.3 |  | D1.4 |  | D1.5 |  | D1.6 |  |  |  | D1.7 |  | D1.8 |  | D1.9 |  | D1.10
IO1.1 | Start-up of all activities
| Description: | Set-up of the governance bodies and operational structure. Preparation of foreseen periodic reports up to B4
| KPI | # of periodic reports submitted
|  | D1.1 | Full set-up of the governance bodies and operational structure
IO1.2 | NFFA-DI Data Management Plan adoption
| Description: | Definition od the NFFA-DI Data Management Plan
| KPI | # of sections included in the DMP (sections are: 1) type and format of research data generated/collected; 2) methodologies and standards followed; 3) organization and storage of data; 4) definition of responsible for the various aspects of the project's data management
|  | D1.2 | Data Management Plan - First release
IO1.3 | Analysis of the activities of the first part of the project
| Description: | Monitoring and analysis of activities carried out in the first part of the project. Preparation of foreseen periodic reports up to B7
| KPI | # of periodic reports submitted
|  | D1.3 | First progress report
IO1.4 | Draft of bylaws of future consortium
| Description: | Proper legal and organizational structure of the consortium for long-term operation of NFFA-DI
| KPI | # of benchmarked European organizations
|  | D1.4 | Consortium agreement for long-term operation
IO1.5 | Identification of the most suited methodologies for the FAIRness of the scientific outcomes
| Description: | Assessment of the methodology for implementing the FAIRness of the scientific outcomes generated by user access. Publications, conference presentations and patents (PPP monitoring) will be used for measuring the success of the awarded access packages.
| KPI | # of in-house data-sets to test the methodology
|  | D1.5 | Specification report of the PPP related data integration in the NFFA-DI FAIR protocols
IO1.6 | Analysis of the activities of the central months of the project
| Description: | Monitoring and analysis of activities carried out in the central months of the project. Preparation of foreseen periodic reports up to B10
| KPI | # of periodic reports submitted
|  | D1.6 | Second progress report
IO1.7 | Definition of the baseline of the scientific outcomes of the RI before upgrade
| Description: | Evaluation of the pre-upgrade scientific outcomes to be used as a reference for the monitoring activity.
| KPI | # of analysed pre-upgrade publications, presentations and patents
|  | D1.7 | Pre-upgrade retrospective monitoring of the NFFA scientific outcomes
IO1.8 | Analysis of activities carried out in the user access start-up phase
| Description: | Monitoring and analysis of activities carried out in the user access start-up phase. Preparation of foreseen periodic reports up to B13
| KPI | # of periodic reports submitted
|  | D1.8 | Third progress report
IO1.9 | Identification of a model for the integration of the NFFA-DI RI in the European context
| Description: | Interaction with the EC, NFFA-Europe and other RIs at European level. Identification of possible opportunities in view of long-term operation within the European context
| KPI | # of strategic discussions at European level
|  | D1.9 | Report on possible opportunities for the NFFA-DI Ri in the European context
IO1.10 | First analysis of the scientific outcomes of the post-upgrade NFFA-DI RI
| Description: | Application to a first set of post-upgrade results of the methodologies previously developed and tested
| KPI | # of monitored post-upgrade results and publications
|  | D1.10 | First post-commissioning monitoring report of the NFFA scientific outcomes

## WP2
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | [11 empty] | 25080 |  | 30096 |  |  |  | 25080 | [12 empty] | 0 | 80256 | 80256 | TECNOL2 M7-18 per tot 12 PM | TECNOL3 M7-14 per un tot di 7,2 PM
CNR-IFN@MI | [19 empty] | 6270 | [10 empty] | 0 | 6270 | 6270 | RIC M19-20 per tot 1,5 PM
CNR-IFN@TN | [30 empty] | 0 | 0 | 0
CNR-IMM@BO | [30 empty] | 0 | 0 | 0
CNR-IMM@CT | [30 empty] | 0 | 0 | 0
CNR-ISM | [30 empty] | 0 | 0 | 0
CNR-NANOTEC | [30 empty] | 0 | 0 | 0
CNR-SPIN | [30 empty] | 0 | 0 | 0
AREA | [7 empty] | 12771 | [22 empty] | 0 | 12771 | 12771 | PM M5-7 per un tot di 3 PM
POLIFAB | [30 empty] | 0 | 0 | 0
UNIMI | [8 empty] | 67100 | [5 empty] | 67100 | [15 empty] | 134200 | 0 | 134200
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12771 | 67100 | 0 | 0 | 25080 | 0 | 30096 | 67100 | 0 | 0 | 25080 | 0 | 6270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134200 | 99297 | 233497
FLUSSO | 0 |  | 0 |  | 0 |  | 12771 |  | 67100 |  | 25080 |  | 30096 |  | 67100 |  | 25080 |  | 6270 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  |  |  | 233497
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 13664.97 |  | 71797 |  | 26835.6 |  | 32202.72 |  | 71797 |  | 26835.6 |  | 6708.9 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 249841.79
IO | [6 empty] | IO2.1 |  | IO2.2 |  | IO2.3 |  | IO2.4 |  | IO2.5 |  | IO2.6 |  | IO2.7
Deliverables | [6 empty] | D2.1 |  | D2.2 |  | D2.3 |  | D2.4 |  | D2.5 |  | D2.6.1 | D2.6.2 | D2.7.1 | D2.7.2
IO2.1 | Procedures for real-time monitoring
| Description: | A new model for continuous real-time monitoring of all user-related activities to optimize the services to users
| KPI | # of compatibility tests on data of NFFA-Europe Pilot project
|  | D2.1 | Protocols for Real time access monitoring, statistics and analytics
IO2.2 | Conceptual design of SEP and Digital catalogue
| Description: | Conceptual design of SEP and Digital catalogue. Contract for SEP development signed. First payment completed.
| KPI | # of sections designed for SEP and digital catalogue
|  | D2.2 | Conceptual design of SEP and Digital catalogue.
IO2.3 | Definition of the digital workflow for access
| Description: | A logical scheme for the Digital Work Flow will be developed for each step of the integrated access workflow: from proposal submission to technical and scientific evaluation, user-provider exchange, access data archiving and access monitoring
| KPI | # of digital workflow steps defined
|  | D2.3 | Logical schemes for the Digital Work Flow and procedures for user access
IO2.4 | Start of activity for the central coordination of the TLNet
| Description: | The Technical Liaison Network (TLNet) is the technical backbone of the distributed infrastructure. A smooth integration of all nodes requires a timely and precise central coordination. The achievement of this IO implies that all schemes and procedures for central coordination are identified and tested through the sharing of information for filling the digital catalogue.
| KPI | # of digital functionalities of the TLNet digital dashboard
|  | D2.4 | TLNet team building and operational modalities
IO2.5 | Online publication of digital catalogue and SEP
| Description: | A Single Entry Point (SEP) for user access will be implemented. Starting from the collection of user data at registration level on the web portal, it will allow proposal drafting, submission, evaluation, scheduling and finally monitoring of access activities. The digital catalogue will be a multi-level compendium of the NFFA-DI offer, including the possibility to access and compare technical specifications of the different instruments. Initial gate to the NFFA-DI RI, it will offer users the possibility to select the most appropriate techniques and methods for the preparation of a comprehensive research proposal through the SEP.
| KPI | # of functionalities of the SEP
| KPI | # of items in the catalogue
|  | D2.5 | First release of online SEP and catalogue
IO2.6 | Definition of interoperability protocols
| Description: | Development of protocols for ensuring interoperability among the different nodes, in view of a multi-disciplinary multi-site execution of complex experimental work-plans.
| KPI | # of standardized procedures shared among the consortium
|  | D2.6.1 | Protocols for sample transfer among nodes
|  | D2.6.2 | Nano-safety protocols
IO2.7 | Setup of scientific evaluation protocols for users' proposals
| Description: | Appointment of Access Review Panel members and chair, identification of a suitable evaluation scheme.
| KPI | # of appointed Access Review Panel members
|  | D2.7.1 | Scientific evaluation working scheme
|  | D2.7.2 | Appointment of first Access review Panel Chair and members

## WP3
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | [8 empty] | 85400 | [9 empty] | 158600 | [8 empty] | 40128 | 97600 |  | 341600 | 40128 | 381728 | TECNOL3 M14-23 per tot 9,6 PM
CNR-IFN@MI | [18 empty] | 18300 | 6270 | [10 empty] | 18300 | 6270 | 24570 | RIC M13-14 per tot 1,5 PM
CNR-IFN@TN | [8 empty] | 18300 | [10 empty] | 16720 | [6 empty] | 24400 |  |  |  | 42700 | 16720 | 59420 | RIC3 M15-18 per tot 4 PM
CNR-IMM@BO | [19 empty] | 8360 | [10 empty] | 0 | 8360 | 8360 | RIC M13-14 per tot 2 PM
CNR-IMM@CT | [9 empty] | 16720 | [9 empty] | 33440 | [10 empty] | 0 | 50160 | 50160 | TECNOL2 M7-18 per tot 12 PM
CNR-ISM | [19 empty] | 4180 | [10 empty] | 0 | 4180 | 4180 | RIC M16 per tot 1 PM
CNR-NANOTEC | [19 empty] | 33440 | [10 empty] | 0 | 33440 | 33440 | RIC3 M18-19 per tot 2PM | TECNOL M18-19 per tot 2PM | RIC1-2 M19-20 per 2 PM ciascuno
CNR-SPIN | [9 empty] | 8360 | [8 empty] | 15860 | 7346.6667 | [10 empty] | 15860 | 15706.6667 | 31566.6667 | RIC1 M7-8 per tot 2 PM | CTER1 M13-14 per tot 2 PM
AREA | [9 empty] | 25542 | [6 empty] | 2074000 | 34056 |  | 8514 | [5 empty] | 25542 |  | 8514 |  |  | 2074000 | 102168 | 2176168 | ENG M2-28 x tot 24 PM
POLIFAB | [9 empty] | 15500 | [8 empty] | 7320 | [11 empty] | 7320 | 15500 | 22820 | TECNOL2 M7-10 per tot 4 PM
UNIMI | [18 empty] | 73200 | [11 empty] | 73200 | 0 | 73200
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103700 | 66122 | 0 | 0 | 0 | 0 | 0 | 0 | 2074000 | 34056 | 273280 | 118270.6667 | 0 | 0 | 0 | 0 | 0 | 25542 | 24400 | 48642 | 97600 | 0 | 2572980 | 292632.6667 | 2865612.6667
FLUSSO | 0 |  | 0 |  | 0 |  | 0 |  | 169822 |  | 0 |  | 0 |  | 0 |  | 2074000 | 34056 | 59135.3333 | 332415.3333 | 0 |  | 0 |  | 25542 |  | 73042 |  | 97600 |  |  |  | 2865612.6667
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 0 |  | 181709.54 |  | 0 |  | 0 |  | 0 |  | 2219180 | 36439.92 | 63274.8067 | 355684.4067 | 0 |  | 0 |  | 27329.94 |  | 78154.94 |  | 104432 |  | 0 |  | 3066205.5533
IO | [8 empty] | IO3.1 | [7 empty] | IO3.2 | IO3.3 | IO3.4 | IO3.5 |  |  |  |  | IO3.6 |  | IO3.7 |  | IO3.8
Deliverables | [8 empty] | D3.1 | [7 empty] | D3.2 | D3.3 | D3.4 | D3.5 |  |  |  |  | D3.6 |  | D3.7 |  | D3.8
IO3.1 | Survey of current FAIRness of RI instrumentation and plan for action
| Description: | The initial situation of NFFA-DI laboratories with respect to FAIRness of the instrumentation will be clarified. A plan for action to improve FAIRness to higher standards will be agreed. First tenders / purchase procedures are completed and advance payments / payments completed after specific invoices.
| KPI | # of laboratories interviewed and instruments catalogued
|  | D3.1 | Report on the FAIRness of tools within the consortium and plan of action
IO3.2 | Upgrade of ORFEO
| Description: | Upgrade of ORFEO data center with additional components in computing/storage and network capabilities. Hardware installed and configured. Invoices paid.
| KPI | % increase of ORFEO storage capacity (max +30%)
| KPI | % increase of ORFEO computational capacity (max +30%)
|  | D3.2 | Report on the upgrade of the ORFEO datacenter
IO3.3 | First release of OFED
| Description: | A first set of basic services will be initially offered, on top of ORFEO infrastructure. It will comprise a first release of a tool to create data management plans and metadata schema editors to help scientists and experimental station owners and deployers to implement a FAIR-by-design approach.
| KPI | # of services offered by OFED
|  | D3.3 | First available release of the OFED Digital Ecosystem and associated report
IO3.4 | Metadata system for OU upgrade
| Description: | Metadata schema for NFFA-DI experimental techniques and instruments will be identified and collected to better define FAIR-by-design implementation.
| KPI | # of metadata schema developed
|  | D3.4 | Report of metadata schema developed and implemented
IO3.5 | First release of FAIR-by-design modules for all OU
| Description: | This first release will comprise a set of modules developed by partners on the instruments that implements FAIR-by-design approach. Related purchase procedures are completed and paid after specific invoices.
| KPI | # of implemented modules
|  | D3.5 | First report on the implemented modules for experimental facilities
IO3.6 | Second release of OFED
| Description: | A second release of the NFFA-DI Overarching Fair Ecosystem for Data System (OFED) will make available a second set of innovative data services. This OFED release comprises the updated version of all services previously installed and provides the final digital ecosystem.
| KPI | # of services offered by OFED
|  | D3.6 | Second release of the OFED Digital Ecosystem
IO3.7 | Second release of FAIR-by-design environment for all OU
| Description: | This second release will enlarge the initial set of modules developed by partners on the instruments that implements FAIR-by-design apprach
| KPI | # of implemented modules
|  | D3.7 | Second report on the implemented modules for experimental facilities
IO3.8 | First set of FAIR-by-design research data
| Description: | Acquired datasets identified with unique Digital Object Identifier (DOI). These could be generated both in-house and from users’ experiments involving one or more instruments available at RI. Last invoices are paid.
| KPI | # of acquired datasets identified with unique Digital Object Identifier (DOI)
|  | D3.8 | Report on the first set of FAIR-by-design research data

## WP4
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | [10 empty] | 1539303.44 | 144400 | 183000 |  |  |  | 658800 | 144400 | 329400 |  |  |  | 170800 | 44080 | 85400 |  | 709703.44 |  | 354851.72 | 44080 | 4031258.6 | 376960 | 4408218.6 | RIC1-2-3-4 M7-18 per tot 12 PM ciascuno |  | CTER1-2 M7-30 per 24 PM ciascuno
CNR-IFN@MI | [10 empty] | 244000 | [10 empty] | 8360 |  |  |  |  | 244000 |  | 122000 |  | 610000 | 8360 | 618360 | RIC M17-19 per tot 2 PM
CNR-IFN@TN | [10 empty] | 414800 | [5 empty] | 414800 | 0 | 207400 |  |  | 50160 | [8 empty] | 1037000 | 50160 | 1087160 | RIC1 M18-22 per tot 6 PM | RIC2 M17-21 per tot 6 PM
CNR-IMM@BO | [10 empty] | 190612.8 | [5 empty] | 190612.8 | 8360 | 95306.4 | [10 empty] | 4180 | 476532 | 12540 | 489072 | RIC M15-16 + M29 per 2+1PM
CNR-IMM@CT | [10 empty] | 1464000 | 16720 | [8 empty] | 138799.4 | 41800 |  |  |  |  | 1464000 | 16720 | 732000 | 25080 | 3798799.4 | 100320 | 3899119.4 | RIC6 M7-30 per tot 24 PM
CNR-ISM | [10 empty] | 76616 | [5 empty] | 76616 | 0 | 38308 | [11 empty] | 191540 | 0 | 191540
CNR-NANOTEC | [10 empty] | 1952000 | [15 empty] | 1952000 | 58520 | 976000 |  | 4880000 | 58520 | 4938520 | RIC3 M21-24 per tot 4 PM | TECNOL M21-24 x 4 PM |  | RIC1-2 M26-28 per tot 3 PM ciascuno
CNR-SPIN | [10 empty] | 622200 | 60800 | 366000 | 16720 |  |  | 622200 | 26726.6667 | 311100 | 47120 | 60512 |  |  | 36733.3333 |  |  |  |  | 0 |  | 1982012 | 188100 | 2170112 | RIC1 M9-M16 per tot 8 PM | RIC2 M12-19 per 8 PM |  | CTER1 M7-12+M15-24 per tot 6+10PM | CTER2 M7-17+M19-24 per tot 11+6 PM
AREA | [10 empty] | 826940.4 | 25542 | 122000 |  |  |  | 244000 | 51084 | 122000 |  |  |  |  | 51084 |  |  | 582940.4 |  | 291470.2 | 51084 | 2189351 | 178794 | 2368145 | RIC1M7-30 per tot 24 PM | TECNOL2 M13-30 per 18 PM
POLIFAB | [10 empty] | 1545008 | 46500 | [9 empty] | 62000 | 183000 | 0 |  |  | 1545008 |  | 772504 |  | 4045520 | 108500 | 4154020 | TECNOL1 M9-20 per tot 12 PM | TECNOL2 M11-20 per tot 10 PM |  | TECNOL3 M7-12 per tot 6 PM
UNIMI | [9 empty] | 9300 | 107360 | 23250 | 158600 | [7 empty] | 122000 | 38750 | 68200 | 7750 |  |  | 107360 | 37200 | 53680 | 23250 | 617200 | 139500 | 756700 | TECNOL1 M7-9+M17-27 per tot 2,4+9,6 PM |  | TEC M7-30 per tot 24 PM
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9300 | 8982840.64 | 317212 | 829600 | 16720 | 0 | 0 | 2207028.8 | 230570.6667 | 1103514.4 | 47120 | 321311.4 | 201070 | 422000 | 139647.3333 | 85400 | 0 | 6605011.84 | 112440 | 3302505.92 | 147674 | 23859213 | 1221754 | 25080967
FLUSSO | 0 |  | 0 |  | 0 |  | 0 |  | 9300 |  | 9300052.64 |  | 846320 |  | 0 |  | 2437599.4667 |  | 1150634.4 |  | 522381.4 |  | 302697.3333 | 258950 | 85400 |  | 6717451.84 |  | 3445999.92 | 4180 | 25080967 |  | 25080967
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 0 |  | 9951 |  | 9951056.3248 |  | 905562.4 |  | 0 |  | 2608231.4293 |  | 1231178.808 |  | 558948.098 |  | 323886.1467 | 277076.5 | 91378 |  | 7187673.4688 |  | 3687219.9144 | 4472.6 | 26836634.69 |  | 26836634.69
IO | [8 empty] | IO4.1 |  | IO4.2 |  | IO4.3 |  |  |  | IO4.4 |  | IO4.5 |  | IO4.6 |  | IO4.7 | IO4.8 | IO4.9 |  | IO4.10 |  | IO4.11 | IO4.12
Deliverables | [8 empty] | D4.1 |  | D4.2 |  | D4.3 |  |  |  | D4.4 |  | D4.5 |  | D4.6 |  | D4.7 | D4.8 | D4.9 |  | D4.10 |  | D4.11 | D4.12
IO4.1 | Complete overview on tender/procurement status
| Description: | As part of Activity A4.2, a complete overview on the status and timeline of all envisaged procurement procedures (via tenders or direct acquisitions) is sketched.
| KPI | # of tender/procurement process started
|  | D4.1 | Report on status of foreseen tender/procurement processes
IO4.2 | Suppliers identified for all tender procedures, orders issued and advance payment (40%) completed
| Description: | For all tenders for acquisition of instrumentation items costing more than 139 keur NET (sopra soglia) , the tender procedure is completed, orders are issued and a 40% advanced payment is completed after specific invoices
| KPI | # of tender procedures completed
| KPI | # of contracts signed after tender completion
| KPI | # of advance payments completed
|  | D4.2 | Report on tender notices, tender assignments and advance payments for instrumentation items above 139 keuro value
IO4.3 | Completion of the acquisition procedures for items under 139 keur (NET) delivered by M12
| Description: | Acquisition procedures completed, instrumentation installed and commissioning completed for instrumentation items below 139 keur NET value that were delivered in the first year of the project. Related invoices paid.
| KPI | # of contracts (sotto soglia) signed
| KPI | # of intruments delivered
| KPI | # of instruments installed
| KPI | # of invoices paid
|  | D4.3 | Report on instrumentation (sotto soglia) delivered and commissioned in the first project year
IO4.4 | Intermediate payment (40%) for instrumentation that passed the factory test by M17
| Description: | Intermediate payment (40%) for instrumentation that passed the factory test by M17, after issuing of specific invoices, and related start of integration work in the laboratories
| KPI | # of successful factory tests
|  | D4.4 | Report on first batch of factory tests
IO4.5 | Installation and commissioning of instruments above 139 keur NET value delivered by M19
| Description: | Installation and commissioning of instruments above 139 keur NET value delivered by M19, balance payments completed
| KPI | # of instruments above 139 keur NET fully paid
|  | D4.5 | Report on installation and commissioning of first batch of ordered instruments above 139 keur NET value
IO4.6 | Preparation of the premises for the new instrumentation
| Description: | Civil infrastructure, reorganization and distribution of the room, integration with existing instruments
| KPI | # of premises prepared
|  | D4.6 | Plan for integration of the new major upgrades in the existing facilities
IO4.7 | Intermediate payment (40%) for instrumentation that passed the factory test in M18-23
| Description: | Intermediate payment (40%) for instrumentation that passed the factory test in M17-M23, after issuing of specific invoices, and related start of integration work in the laboratories
| KPI | # of successful factory tests
|  | D4.7 | Report on second batch of factory tests
IO4.8 | Completion of the acquisition procedures for items under 139 keur (NET) delivered after M12
| Description: | Acquisition procedures completed, instrumentation installed and commissioning completed for instrumentation items below 139 keur NET value that were delivered in the second year of the project. Related invoices paid.
| KPI | # of contracts (sotto soglia) signed
| KPI | # of intruments delivered
| KPI | # of instruments installed
| KPI | # of invoices paid
|  | D4.8 | Report on instrumentation (sotto soglia) delivered and commissioned in the second project year
IO4.9 | Installation and commissioning of instruments above 139 keur NET value delivered in M20-25
| Description: | Installation and commissioning of instruments above 139 keur NET value delivered in M20-25, balance payments completed
| KPI | # of instruments above 139 keur NET fully paid
|  | D4.9 | Report on installation and commissioning of second batch of ordered instruments above 139 keur NET value
IO4.10 | Intermediate payment (40%) for instrumentation that passed the factory test in M24-28
| Description: | Intermediate payment (40%) for instrumentation that passed the factory test in M24-M28, after issuing of specific invoices, and related start of integration work in the laboratories
| KPI | # of successful factory tests
|  | D4.10 | Report on third batch of factory tests
IO4.11 | Installation and commissioning of all remaining instruments
| Description: | Installation and commissioning of all other ordered instruments above 139 keur NET value, balance payments completed
| KPI | # of instruments above 139 keur NET fully paid
|  | D4.11 | Report on installation and commissioning of third batch of ordered instruments above 139 keur NET value
IO4.12 | Definition of the needs for a constant technical upgrade of the facilities
| Description: | Analysis of possible synergies among nodes, identification of constant upgrade needs and plans for the 10-year operation phase per INSTALLATION
| KPI | # of needs identified
|  | D4.12 | Report on needs for the long-term technical upgrade of the infrastructure

## WP5
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | [29 empty] | 30096 | 0 | 30096 | 30096 | TECNOL3 M23-30 per tot 7,2 PM
CNR-IFN@MI | [17 empty] | 6270 | [12 empty] | 0 | 6270 | 6270 | RIC M16-17 per tot 1,5 PM
CNR-IFN@TN | [23 empty] | 25080 | [6 empty] | 0 | 25080 | 25080 | RIC3 M19-24 per tot 6 PM
CNR-IMM@BO | [17 empty] | 8360 | [12 empty] | 0 | 8360 | 8360 | RIC M17-18 per tot 2 PM
CNR-IMM@CT | [23 empty] | 25080 | [5 empty] | 25080 | 0 | 50160 | 50160 | TECNOL2 M19-30 per tot 12 PM
CNR-ISM | [17 empty] | 8360 | [12 empty] | 0 | 8360 | 8360 | RIC M17-18 per tot 2 PM
CNR-NANOTEC | [19 empty] | 8360 | [10 empty] | 0 | 8360 | 8360 | RIC3 M20 per tot 1 PM | TECNOL M20 per tot 1 PM
CNR-SPIN | [12 empty] | 4270 |  |  |  |  | 3673.3233 |  | 20900 | [10 empty] | 4270 | 24573.3233 | 28843.3233 | RIC1 M17-20 per tot 4 PM | RIC3 M19 per tot 1 PM | CTER2 M18 per 1 PM
AREA | [17 empty] | 17028 | [5 empty] | 25542 | [5 empty] | 25542 | 0 | 68112 | 68112 | RIC2 M15-30 per tot 16 PM
POLIFAB | [13 empty] | 7750 | [16 empty] | 0 | 7750 | 7750 | TECNOL3 M13-14 per tot 2 PM
UNIMI | [17 empty] | 9300 | [12 empty] | 0 | 9300 | 9300 | TECNOL1 M15-17 per tot 2,4 PM
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4270 | 7750 | 0 | 0 | 0 | 52991.3233 | 0 | 29260 | 0 | 0 | 0 | 75702 | 0 | 0 | 0 | 0 | 0 | 80718 | 4270 | 246421.3233 | 250691.3233
FLUSSO | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12020 |  | 0 |  | 26495.6617 | 26495.6617 | 29260 |  | 0 |  | 75702 |  | 0 |  | 0 |  | 80718 |  |  |  | 250691.3233
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 12861.4 |  | 0 |  | 28350.358 | 28350.358 | 31308.2 |  | 0 |  | 81001.14 |  | 0 |  | 0 |  | 86368.26 |  | 0 |  | 268239.716
IO | [12 empty] | IO5.1 |  |  |  | IO5.2 | IO5.3 | IO5.4 |  |  |  | IO5.5 | [5 empty] | IO5.6
Deliverables | [12 empty] | D5.1 |  |  |  | D5.2 | D5.3 | D5.4 |  |  |  | D5.5 | [5 empty] | D5.6
IO5.1 | Completion of the TLNet structure
| Description: | The TLNet is structured in a central coordinating node and local nodes at the premises of provider nodes. In case of big provider nodes, offering several installations with many techniques, can be structured with more local contacts, in charge to provide technical information and evaluations for group or even single instruments. The achievement of this IO means that all the structures of the TLNet, overall network as well as local node structures is completed, in order to be ready to supply all the technical support necessary for operational implementation of the digital catalogue and of the interoperability protocols for both pre-upgrade and upgraded/new instrumentation.
| KPI | # of appointed TLNet members
|  | D5.1 | TLNet structure
IO5.2 | Technical information for pre-upgrade instrumentation uploaded in the digital catalogue
| Description: | The local TLNet contacts are expected to provide all the necessary technical information and specification and operational data of pre-upgrade instrumentation to be included in the SEP and in the Digital Catalogue. At this phase the first level of the Catalogue navigation (group of techniques overview) and second level (technique brief description and location) must be completed for all the offered methods and services.
| KPI | # of pre-upgrade entries in the catalogue
|  | D5.2 | Digital catalogue of pre-upgrade instrumentation
IO5.3 | Personalized laboratory DMPs
| Description: | Data Management Plans at laboratory level.
| KPI | # of completed laboratory DMPs
|  | D5.3 | Second release of the Data Management Plan including the first batch of laboratory DMPs
IO5.4 | First test call for access
| Description: | First call for users’ access, to be considered as stress test of the fully Digital distributed infrastructure.
| KPI | # of submitted proposals
|  | D5.4 | Report on first test call for access
IO5.5 | Technical information for a first set of upgraded/new instruments uploaded in the digital catalogue
| Description: | The local TLNet contacts are expected to provide all the necessary technical information and specification and commissioning data of upgraded/new instrumentation already installed, to be included in the SEP and in the Digital Catalogue. At this phase, all the 3 levels of the Catalogue navigation, therefore including also the detailed technical specification of the instruments are included in the Catalogue.
| KPI | # of upgraded entries in the catalogue
|  | D5.5 | Digital catalogue of post-upgrade instrumentation
IO5.6 | Second test call for access
| Description: | Second test call for access, building on the analysis of results of the first call and trying to smoothen all the mechanisms.
| KPI | # of submitted proposals
|  | D5.6 | Report on second test call for access

## WP6
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | [15 empty] | 50160 | [11 empty] | 50160 |  |  | 0 | 100320 | 100320 | RIC7 M5-28 per tot 24 PM
CNR-IFN@MI | [30 empty] | 0 | 0 | 0
CNR-IFN@TN | [30 empty] | 0 | 0 | 0
CNR-IMM@BO | [30 empty] | 0 | 0 | 0
CNR-IMM@CT | [30 empty] | 0 | 0 | 0
CNR-ISM | [30 empty] | 0 | 0 | 0
CNR-NANOTEC | [30 empty] | 0 | 0 | 0
CNR-SPIN | [30 empty] | 0 | 0 | 0
AREA | [11 empty] | 25542 | [5 empty] | 34056 | [5 empty] | 25542 |  |  |  | 42570 |  | 25542 | 0 | 153252 | 153252 | PM M17-M28 per tot 12 PM | TECNOL1 M7-30 per tot 24 PM
POLIFAB | [30 empty] | 0 | 0 | 0
UNIMI | [30 empty] | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25542 | 0 | 0 | 0 | 50160 | 0 | 34056 | 0 | 0 | 0 | 0 | 0 | 25542 | 0 | 0 | 0 | 92730 | 0 | 25542 | 0 | 253572 | 253572
FLUSSO | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 25542 |  | 0 |  | 50160 |  | 25542 | 8514 | 0 |  | 0 |  | 25542 |  | 0 |  | 50160 | 42570 | 12771 | 12771 | 253572 |  | 253572
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 27329.94 |  | 0 |  | 53671.2 |  | 27329.94 | 9109.98 | 0 |  | 0 |  | 27329.94 |  | 0 |  | 53671.2 | 45549.9 | 13664.97 | 13664.97 | 271322.04 |  | 271322.04
IO | [10 empty] | IO6.1 |  |  |  | IO6.2 |  | IO6.3 | IO6.4 |  |  |  |  | IO6.5 |  |  |  | IO6.6 | IO6.7 | IO6.8 | IO6.9
Deliverables | [10 empty] | D6.1 |  |  |  | D6.2 |  | D6.3 | D6.4 |  |  |  |  | D6.5 |  |  |  | D6.6 | D6.7 | D6.8 | D6.9
IO6.1 | Design of the IRA procedures
| Description: | The objective focuses on the definition of terms and conditions to access IRA with the definition of the cost models to give evidence of operating running costs each Partner will incur.
| KPI | # of cost models defined
|  | D6.1 | Report and specification document of the Protocol of IRA procedures
IO6.2 | Graphical interfaces for simulation tools for NFFA-DI community
| Description: | The goal of Activity 6.6 is to develop new software, graphical tools and interfaces to facilitate the use of theoretical approaches based on density functional theory. The target users of these tools are experimental groups performing measurements at NFFA-DI. This first objective is the successful development of graphical interfaces to enable the user-friendly set up of input files, structure generation and structure editing.
| KPI | # of graphical tools in the interface application
|  | D6.2 | Report on graphical interfaces for simulation tools
IO6.3 | Virtual Access Services 1 : Semi-automatic classification service
| Description: | Develop tools for retrieval of several advanced features including, but not limited to, tools to sort/group images by similarity, size to organize it in structured DB
| KPI | # of datasets automatically classified
|  | D6.3 | Design of the semi-automatic classification service
IO6.4 | Helpdesk Set Up
| Description: | The focus of the IO is to setup the helpdesk. The function of the Helpdesk is crucial to raise awareness on technology transfer strategies to exploit NFFA-DI research results and bring academic inventions to the market.
| KPI | # of researchers asking advisory services to the Helpdesk (target 10 at BIM15)
|  | D6.4 | IP&M Helpdesk guidelines
IO6.5 | IRA guideline
| Description: | The spefication will be implemented in a set of IRA procedures. The IRA guideline will allow the community to understand structures, tools and procedures implemented and made available.
| KPI | # of OUs adopting IRA platforms
|  | D6.5 | Report and specification document of the Protocol of IRA procedures
IO6.6 | Standardized simulation workflows for NFFA-DI community for standard properties calculations
| Description: | The goal of Activity 6.6 is to develop new software, graphical tools and interfaces to facilitate the use of theoretical approaches based on density functional theory. The target users of these tools are experimental groups performing measurements at NFFA-DI. This second objective is the successful design of computational recipies and workflows to simulate a variety of experimental measurements (i.e. STM images, ARPES, …).
| KPI | # of experimental techniques/systems addressed with the developed workflows
|  | D6.6 | Report on graphical interfaces for simulation tools
IO6.7 | Setup of the Digital portfolio
| Description: | The“Digital Portfolio” represents the essential tool to decline NFFA-DI offer for the business world, allowing the development of applied research projects. Investigation potentiality is organized in its possible industrial applications (including case studies), in order to guide and support companies in identifying, choosing and applying for both stand-alone services and multi-technique investigations offered by NFFA-DI.
| KPI | # of services identified (target >5)
|  | D6.7 | Report on the installation the Portfolio
IO6.8 | Virtual Access Services 2 : Ready-to-use Neural Networks
| Description: | Deployment of deep learning algorithms for image analysis and/or automatic classification
| KPI | # of instruments for which deep learning algorithms, aimed at facilitating usage, are designed and deployed
|  | D6.8 | Report on ready-to-use Neural Networks for scientific image classification
IO6.9 | AI-augmented research infrastructure facility available
| Description: | The main objective of Activity 6.5 will be, in the top of the upgraded Orfeo computational facility to establish an AI- augmented research infrastructure that enables the experimental stations of NFFA-DI to exploit state-of-the- art machine learning algorithms for nanoscience and materials.
| KPI | # of experimental sources successfully considered for advanced ML analysis on multiplexing data
|  | D6.9 | Report on the AI-augmented research infrastructure

## WP7
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | [17 empty] | 50160 |  |  |  |  | 101260 | 175560 | [5 empty] | 125400 | 101260 | 351120 | 452380 | TECNOL2 M19-30 per tot 12 PM | RIC1-2-3-4 M19-30 per tot 12 PM ciascuno |  | RIC5-6 M13-24 per tot 12 PM ciascuno
CNR-IFN@MI | [23 empty] | 16720 | [6 empty] | 0 | 16720 | 16720 | RIC M21-24 per tot 4 PM
CNR-IFN@TN | [27 empty] | 25080 |  | 37620 | 0 | 62700 | 62700 | RIC1 M23-28 per tot 6 PM | RIC2 M22-30 per tot 9PM
CNR-IMM@BO | [11 empty] | 20900 | [15 empty] | 37620 |  |  | 0 | 58520 | 58520 | RIC M8-12 + M19-27 per tot 5 + 9 PM
CNR-IMM@CT | [11 empty] | 75240 |  |  |  |  | 134200 | 125400 | [5 empty] | 150480 | [5 empty] | 150480 | 134200 | 501600 | 635800 | TECNOL3 M19-30 per tot 12 PM | RIC1-2-3 M7-30 per tot 24 PM ciascuno |  | RIC4-5 M13-30 per tot 18 PM ciascuno
CNR-ISM | [27 empty] | 37620 |  |  | 0 | 37620 | 37620 | RIC M19-27 per tot 9 PM
CNR-NANOTEC | [27 empty] | 75240 |  | 16720 | 0 | 91960 | 91960 | RIC3 M25-28 per tot 4 PM | TECNOL M25-28 per tot 4 PM |  | RIC1-2 M21-25+M29-30 per tot 5+2 PM
CNR-SPIN | [11 empty] | 45980 |  |  |  |  | 36600 | 25080 | [5 empty] | 50160 |  |  |  | 33440 |  | 69160 | 36600 | 223820 | 260420 | RIC1 M23-24+25-30 per tot 2+6 PM | RIC2 M7-11+20-28 per tot 5+9 PM |  | RIC3 M7-18+M20-28 per tot 12+9 PM | CTER1 M25-30 per tot 6 PM | CTER2 M25-30 per tot 6 PM
AREA | [27 empty] | 34056 |  |  | 0 | 34056 | 34056 | RIC2 M7-14 per tot 8 PM
POLIFAB | [17 empty] | 15500 |  |  |  |  | 25010 | 54250 |  |  |  | 15500 | 7320 | 46500 | 32330 | 131750 | 164080 | TECNOL1 M21-M30 per tot 10 PM | TECNOL2 M21-30 per tot 10 PM |  | TECNOL3 M15-M28 per tot 14 PM
UNIMI | [11 empty] | 23250 | [5 empty] | 46500 | [5 empty] | 23250 | [5 empty] | 37200 | 0 | 130200 | 130200 | TECNOL1 M9-15+M26-30 per tot 6+3,6 PM |  | TECNOL2 M7-30 per tot 24 PM
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 165370 | 0 | 0 | 0 | 0 | 170800 | 262640 | 0 | 0 | 0 | 0 | 126270 | 470420 | 0 | 0 | 0 | 258556 | 7320 | 483080 | 304390 | 1640066 | 1944456
FLUSSO | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 165370 |  | 0 |  | 0 |  | 433440 |  | 0 |  | 0 |  | 596690 |  | 0 |  | 258556 |  | 490400 |  |  |  | 1944456
FLUSSO incl. OH | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 176945.9 |  | 0 |  | 0 |  | 463780.8 |  | 0 |  | 0 |  | 638458.3 |  | 0 |  | 276654.92 |  | 524728 |  | 0 |  | 2080567.92
IO | [10 empty] | IO7.1 | [5 empty] | IO7.2 | [5 empty] | IO7.3 |  |  |  | IO7.4 |  | IO7.5
Deliverables | [10 empty] | D7.1 | [5 empty] | D7.2 | [5 empty] | D7.3.1 | D7.3.2 |  |  | D7.4 |  | D7.5
IO7.1 | Organization and start of the purchase procedure for innovative equipment
| Description: | An overview on the modalities, status and timeline of all envisaged procurement procedures is sketched.
| KPI | # of tender/procurement processes started
|  | D7.1 | Report on tenders/procurement procedures for innovative instrumentation
IO7.2 | First deliveries of instrumentation for exploratory research, protocol design and innovative methods
| Description: | First acquisition procedures completed, instrumentation installed and commissioning completed. Invoices paid.
| KPI | # of intruments delivered
| KPI | # of instruments installed
| KPI | # of invoices paid
|  | D7.2 | First report on instrumentation delivered and commissioned for exploratory research
IO7.3 | Further deliveries of instrumentation for innovative research, start-up of research activities for all OU
| Description: | Further acquisition procedures completed, instrumentation installed and commissioning completed for all instrumentation. Invoices paid. Upskill and exploratory research started.
| KPI | # of instruments delivered
| KPI | # of instruments installed
| KPI | # of invoices paid
| KPI | # of research activities with new instrumentation started (experiments/methodological developments planned or training sessions on similar equipment ongoing)
|  | D7.3.1 | Second report on instrumentation delivered and commissioned for exploratory research
|  | D7.3.2 | First report on upskill/exploratory research activities
IO7.4 | Start of research with the new instrumentation/developments
| Description: | Test experiments pushing to the limit the performances of the new instruments/methods. Round-robin tests of the new instrumentation with complementary resources of the RI.
| KPI | # of test experiments with upgraded instrumentation/methods
|  | D7.4 | First report on upskill of staff on usage of upgraded instrumentation/methods
IO7.5 | Completion of innovative research test activities for the use of the new instrumentation
| Description: | Test activities for innovative research making use of the new instrumentation and newly developed methods are completed as in-house research, in order to simulate the future user proposal needs. Tests of interoperability are completed.
| KPI | # of laboratories with upgraded instrumentation ready to provide user access
|  | D7.5 | Second report on upskill of staff on usage of upgraded instrumentation

## WP8
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | B1-15 |  | TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | 0 | [11 empty] | 15000 | [5 empty] | 7100 |  |  |  | 7100 |  | 7100 |  |  |  | 7100 |  | 43400 | 0 | 43400
CNR-IFN@MI | [19 empty] | 6270 | [10 empty] | 0 | 6270 | 6270 | RIC M14-15 per tot 1,5 PM
CNR-IFN@TN | [18 empty] | 14200 | [5 empty] | 14200 | 8360 |  |  |  |  | 28400 | 8360 | 36760 | RIC3 M25-26 per tot 2 PM
CNR-IMM@BO | [18 empty] | 7100 | 4180 |  |  |  |  | 7100 |  |  |  |  | 4180 | 14200 | 8360 | 22560 | RIC M30 per 2 PM
CNR-IMM@CT | [18 empty] | 49424.9 |  |  |  | 14121.4 |  | 7060.7 |  |  |  | 14121.4 |  | 84728.4 | 0 | 84728.4
CNR-ISM | [18 empty] | 7100 | [5 empty] | 7100 | [5 empty] | 14200 | 0 | 14200
CNR-NANOTEC | [29 empty] | 8360 | 0 | 8360 | 8360 | RIC3 M29 per 1 PM | TECNOL M29 per 1 PM
CNR-SPIN | [18 empty] | 21750 |  |  |  |  | 8360 | 21750 |  |  |  |  | 16720 | 43500 | 25080 | 68580 | RIC1 M21-22 per tot 2 PM |  | RIC2 M29-30 per tot 2PM | RIC3 M29-30 per tot 2PM
AREA | [18 empty] | 50000 | [5 empty] | 50000 | [5 empty] | 100000 | 0 | 100000
POLIFAB |  |  |  |  | 151533.52 |  |  | 7750 |  |  |  |  | 15000 | [16 empty] | 7750 | 166533.52 | 15500 | 182033.52 | TECNOL1 M7-8 per tot 2 PM |  | TECNOL3 M29-30 per tot 2 PM
UNIMI |  |  |  |  | 98980 | [7 empty] | 15000 | [17 empty] | 113980 | 0 | 113980
TOTAL | 0 | 0 | 0 | 0 | 250513.52 | 0 | 0 | 7750 | 0 | 0 | 0 | 0 | 45000 | 0 | 0 | 0 | 0 | 0 | 156674.9 | 10450 | 0 | 0 | 21221.4 | 8360 | 114310.7 | 8360 | 0 | 0 | 21221.4 | 37010 | 608941.92 | 71930 | 680871.92
FLUSSO | 0 |  | 0 |  | 250513.52 |  | 7750 |  | 0 |  | 0 |  | 45000 |  | 0 |  | 0 |  | 167124.9 |  | 0 |  | 29581.4 |  | 122670.7 |  | 0 |  | 29115.7 | 29115.7 |  |  | 680871.92
FLUSSO incl. OH | 0 |  | 0 |  | 268049.4664 |  | 8292.5 |  | 0 |  | 0 |  | 48150 |  | 0 |  | 0 |  | 178823.643 |  | 0 |  | 31652.098 |  | 131257.649 |  | 0 |  | 31153.799 | 31153.799 | 0 |  | 728532.9544
IO |  |  |  |  | IO8.1 |  | IO8.2 | [5 empty] | IO8.3 | [5 empty] | IO8.4 |  |  |  | IO8.5 |  | IO8.6 |  |  |  | IO8.7 | IO8.8
Deliverables |  |  |  |  | D8.1 |  | D8.2 | [5 empty] | D8.3 | [5 empty] | D8.4 |  |  |  | D8.5 |  | D8.6 |  |  |  | D8.7 | D8.8
IO8.1 | Financing PhD positions
| Description: | Financing (2-years) of PhD positions at Universities co-located with the Consortium nodes, selection of winners and attribution to NFFA-DI nodes for carrying out their research programme in nanoscience
| KPI | # of identified PhD profiles
|  | D8.1 | Identification and approval by PhD schools of the NFFA-DI PhD profiles
IO8.2 | Start of training programme
| Description: | Start of training programmes in all laboratories for young scientists including short exchange visits among the RI nodes to keep close contacts among all trainees and favour team building
| KPI | # of planned training actions
|  | D8.2 | Terms of reference for the training programme
IO8.3 | Acceptance to RITRAIN school
| Description: | Application to the RETRAIN school of Research Infrastructure managers held by Univ. Milano Bicocca in connection with the EC-project RITRAIN-Plus. The school is addressed to future RI managers as well as to experienced practitioners of RI services. It can deliver a master certificate
| KPI | # of NFFA-DI people accepted to the Retrain school
|  | D8.3 | Enrolment of NFFA-DI people to the Retrain school
IO8.4 | First level training of data stewards
| Description: | First level training of data stewards: from developing DMPs at single laboratory level to application of the FAIR concept for in-house research.
| KPI | # of data steward trainees
|  | D8.4 | First progress report on data steward training
IO8.5 | Second level training of data stewards: user support
| Description: | Second level training of data stewards: FAIR-data services from EOSC and other relevant data infrastructures and possible development of user interfaces for guiding to these services.
| KPI | # of data steward trainees
|  | D8.5 | Second progress report on data steward training
IO8.6 | Start of laboratory support by data stewards
| Description: | Engagement of data stewards for implementing DMPs at all provider laboratory; user training for guiding to FAIR-data production and for exploiting FAIR-data services from EOSC and other relevant data infrastructures.
| KPI | # of data steward trainees
|  | D8.6 | Third progress report on data steward training
IO8.7 | User support by data stewards
| Description: | User assistance by data stewards for generating FAIR data sets from their research at the NFFA-DI facilities.
| KPI | # of data steward trainees
|  | D8.7 | Fourth progress report on data steward training
IO8.8 | Training of users and young researchers for the usage of the upgraded RI
| Description: | Training of users and young researchers for the usage of the new acquired instrumentation and for the maximum exploitation of its performances; training of users for the FAIR-by-design technology installed also on existing laboratory instruments.
| KPI | # of trainees
|  | D8.8 | Report on training activities on the upgraded RI

## All WPs
| B1 |  | B2 |  | B3 |  | B4 |  | B5 |  | B6 |  | B7 |  | B8 |  | B9 |  | B10 |  | B11 |  | B12 |  | B13 |  | B14 |  | B15 |  | TOTAL |  | OVERALL | Indirect | GRAND TOTAL
| acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale | acquisti | personale
CNR-IOM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58746.6667 | 85400 | 0 | 1539303.44 | 169480 | 198000 | 118216 | 0 | 50160 | 658800 | 219640 | 495100 | 88120 | 0 | 0 | 279160 | 219640 | 92500 | 88120 | 709703.44 | 119661.3333 | 459551.72 | 199576 | 4517518.6 | 1331360 | 5848878.6 | 409421.502 | 6258300.102 | TECNOL1 M5-28 x 24 PM | IM M5-28 x 24 PM | FUNZ M5-28 x 24 PM |  | TECNOL2 M7-30 per 24 PM |  |  | TECNOL3 M7-30 x 24 PM |  | RIC1-2-3-4 M7-30 x 24 PM |  | CTER1-2 M7-30 x 24 PM | RIC5-6 M13-24 x 12 PM | RIC7 M5-28 x 24 PM
CNR-IFN@MI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244000 | 0 | 0 | 0 | 0 | 0 | 0 | 6270 | 18300 | 18810 | 0 | 8360 | 0 | 16720 | 0 | 0 | 244000 | 0 | 122000 | 0 | 628300 | 50160 | 678460 | 47492.2 | 725952.2 | RIC M13-24 x 12 PM
CNR-IFN@TN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18300 | 0 | 414800 | 0 | 0 | 0 | 0 | 0 | 414800 | 0 | 221600 | 16720 | 0 | 50160 | 0 | 25080 | 14200 | 8360 | 24400 | 25080 | 0 | 37620 | 1108100 | 163020 | 1271120 | 88978.4 | 1360098.4 | RIC1 M18-28 x 12 PM | RIC2 M17-30 x 24 PM | RIC3 M15-26 x 12 PM
CNR-IMM@BO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190612.8 | 20900 | 0 | 0 | 0 | 0 | 190612.8 | 16720 | 102406.4 | 12540 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 37620 | 0 | 8360 | 490732 | 96140 | 586872 | 41081.04 | 627953.04 | RIC M8-30 x 23 PM
CNR-IMM@CT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16720 | 1464000 | 91960 | 0 | 0 | 0 | 0 | 134200 | 150480 | 49424.9 | 33440 | 138799.4 | 41800 | 14121.4 | 200640 | 7060.7 | 0 | 1464000 | 16720 | 746121.4 | 225720 | 4017727.8 | 777480 | 4795207.8 | 335664.546 | 5130872.346 | TECNOL1 M13-30 x 18 PM | TECNOL2 M7-30 x 24 PM | TECNOL3 M19-30 x 12 PM |  | RIC1-2-3 M7-30 x 24 PM |  | RIC4-5 M13-30 x 18 PM |  | RIC6 M7-30 x 24PM
CNR-ISM | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76616 | 0 | 0 | 0 | 0 | 0 | 76616 | 8360 | 45408 | 4180 | 0 | 0 | 0 | 0 | 7100 | 0 | 0 | 37620 | 0 | 0 | 205740 | 50160 | 255900 | 17913 | 273813 | RIC M6-27 x 12 PM
CNR-NANOTEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1952000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41800 | 0 | 0 | 0 | 0 | 0 | 0 | 1952000 | 133760 | 976000 | 25080 | 4880000 | 200640 | 5080640 | 355644.8 | 5436284.8 | RIC3 M18-29 x 12 PM | TECNOL M18-29 x 12 PM |  | RIC1-2 M19-30 x 12 PM
CNR-SPIN | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8360 | 622200 | 106780 | 370270 | 16720 | 0 | 0 | 658800 | 55479.99 | 348710 | 75366.6667 | 60512 | 0 | 0 | 95253.3333 | 21750 | 0 | 0 | 33440 | 0 | 85880 | 2082242 | 477279.99 | 2559521.99 | 179166.5393 | 2738688.5293 | RIC1 M7-30 x 24 PM | RIC2 M7-30 x 24 PM | RIC3 M7-30 x 24 PM |  | CTER1 M7-30 x 24 PM |  | CTER2 M7-30 x 24 PM
AREA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12771 | 0 | 38313 | 826940.4 | 51084 | 122000 | 0 | 0 | 25542 | 2318000 | 136224 | 172000 | 8514 | 0 | 0 | 0 | 102168 | 50000 | 25542 | 582940.4 | 85140 | 291470.2 | 102168 | 4363351 | 587466 | 4950817 | 346557.19 | 5297374.19 | PM M5-28 x 24 PM | ENG M5-28 x 24 PM | TECNOL1 M7-30 x 24 PM |  |  | RIC1 M7-30 x 24 PM |  | TECNOL2 M13-30 per tot 18 PM |  |  | RIC2 M7-30 x 24 PM
POLIFAB | 0 | 0 | 0 | 0 | 151533.52 | 0 | 0 | 7750 | 0 | 15500 | 1545008 | 46500 | 15000 | 7750 | 0 | 0 | 0 | 15500 | 7320 | 0 | 0 | 62000 | 208010 | 54250 | 0 | 0 | 1545008 | 15500 | 779824 | 54250 | 4251703.52 | 279000 | 4530703.52 | 317149.2464 | 4847852.7664 | TECNOL1 M7-30 x 24 PM | TECNOL2 M7-30 x 24 PM | TECNOL3 M7-30 x 24 PM
UNIMI | 0 | 0 | 0 | 0 | 98980 | 0 | 0 | 0 | 67100 | 9300 | 107360 | 46500 | 173600 | 0 | 67100 | 0 | 0 | 55800 | 73200 | 0 | 122000 | 38750 | 68200 | 31000 | 0 | 0 | 107360 | 37200 | 53680 | 60450 | 938580 | 279000 | 1217580 | 85230.6 | 1302810.6 | TECNOL1 M7-30 x 24 PM | TEC M7-30 x 24 PM | TECNOL2 M7-30 x 24 PM
TOTAL | 0 | 0 | 0 | 0 | 250513.52 | 0 | 0 | 79267.6667 | 170800 | 88193 | 8982840.64 | 533204 | 878870 | 142686 | 67100 | 75702 | 4451828.8 | 664473.99 | 1533469.3 | 299490.6667 | 321311.4 | 201070 | 569491.4 | 744751.3333 | 199710.7 | 122022 | 6629411.84 | 541741.3333 | 3428647.32 | 799104 | 27483994.92 | 4291705.99 | 31775700.91 | 2224299.0637 | 33999999.9737
FLUSSO | 0 |  | 0 |  | 250513.52 |  | 79267.6667 |  | 258993 |  | 9516044.64 |  | 1021556 |  | 142802 |  | 5116302.79 |  | 1832959.9667 |  | 522381.4 |  | 1314242.7333 |  | 321732.7 |  | 7171153.1733 |  | 4227751.32 |  | 31775700.91 |  | 33999999.9737 |  | 33999999.9737
FLUSSO incl. OH | 0 |  | 0 |  | 268049.4664 |  | 84816.4033 |  | 277122.51 |  | 10182167.7648 |  | 1093064.92 |  | 152798.14 |  | 5474443.9853 |  | 1961267.1643 |  | 558948.098 |  | 1406239.7247 |  | 344253.989 |  | 7673133.8955 |  | 4523693.9124 |  | 33999999.9737